## Sheet1
Neil Scott (information provided on behalf of Dave Hextell, Head of ICT Systems Development) |  |  |  |  | (Last updated: | 10/02/2015)
Project / Activity - Integration | Category | Resource | Planned Completion | On ICT Request List? | Priority | Status | Update & Comments
Integration
Carefusion - Respiratory |  | tbc |  | Yes
Endobase - Endoscopy |  | tbc |  | Yes
Badgernet - Maternity, outstanding issue with UG message |  | NS/JD |  | Yes |  |  | All requested interfaces complete
Radiology - order comms integration, extended alerting |  | tbc |  | No
Radiology - order comms integration, from MSS |  | NS |  | No |  |  | Being testing by service
MSS - automated admissions (PMS) |  | SS/GL | In progress |  |  |  | Input required from service
MPI - bypass HISS |  | tbc |  | No
Carelink - AKI/ADT/Condition alerting |  | tbc |  | No
ADT sequencing issue (PMS) |  | DH
Concerto integration and decommission of iCare |  | NS | Q2
CLIMATE - sexual health integration |  | NS/IZ
Alerting
Review of ED alerting |  | NS/MR | Dec | No
Winter pressures - Birmingham Community [same as Virtual Ward] |  | NS/MR | ASAP | Yes
Reporting
EP "self-service" reporting |  | SM | Q4 | No
Timely TTO |  | MR | Nov | No |  |  | Awaiting review of latest version
Clinical Letters performance |  | NS/MR | Nov | No |  |  | Awaiting review of latest version
Radiology NPSA compliance reporting |  | NR/MR | Q3 | No
Transfer of Care |  | MK |  |  |  |  | Awaiting signoff of latest modification
Radiology recall |  | NS | Q4 |  |  |  | Final reconcilliation of datasets to be completed
Delioittes MSK data warehouse |  | NS/MR
Development
Smoking cessation CQUIN |  | MR |  | Yes |  |  | Ready to go live
Reference files Master - transfer functionality from HISS (PMS) |  | tbc
Case Note Tracking - transfer functionality from HISS (PMS) |  | tbc
Transfer of Care |  | MK |  | No
eJONAH |  | NS/MK |  | No |  |  | Ongoing
METRICS - update |  | NS |  | No |  |  | Awaiting review of latest version
Breast Recall database development/reporting |  | NS |  | No |  |  | In progress, all outstanding datasets built
DNAR |  | MK |  | No |  |  | On hold with service
Nursing eDocumentation |  | MK |  | No |  |  | Full review to take place Feb/Mar/Apr as development was completed 12+ months ago
Diagnostic referral - Cardiology x 6 |  | MK/BD | Nov | Yes |  |  | 2 referral forms being pilotted, 4 further in development
Referral form - Community IV therapy |  | NS/BD |  | Yes
Diagnostic referral - Oesophageal lab |  | NS |  | Yes
EPH - database review |  | NS |  | No |  |  | Ongoing
EPH - GHH Labour Ward modifications |  | NS | Nov | No |  |  | First set of modifications complete, service to provide "wish list"
Radiology recall |  | NS |  | No
HEARTSOL application form |  | SY | Nov | Yes
Gifts/Gratuities DB |  | NS | Nov | No
Modify Pathway Message from ADT System to include fields needed to annotate pathway in Organiser |  | SS
Diabetes IP referral |  | NS |  |  |  |  | Presented at GHH diabetes meeting 09.02, awaiting final feedback
Nursing TV Electronic Root Cause Analysis (RCA) |  | NS
Nursing Falls Electronic Root Cause Analysis (RCA) |  | Ns
EPH/PMS ward management tools |  | MK
Live capacity planning dashboard |  | NS/MK
Scanned Medical Records
IDEAGEN - document loader |  | SY | Q4 | No
OCR - meta data ingestion |  | SY | Q4 | No
Viewer - version to pull from DartKW |  | SY | Q4 | No
Other
Test Your Care - HSE |  | NS/MK | Q4 | No
Deloittes - Diabetes project, extension for other conditions |  | NS/MR | Q4 | No
Jonathan Daniels (information provided on behalf of Dave Hextell, Head of ICT Systems Development) |  |  |  |  | (Last updated: | 12/02/2015)
Project / Activity - Systems Development | Category | Resource | Planned Completion | On ICT Request List? | Priority | Status | Update & Comments
UltraGenda
Audiology UG go-live | Project | SL |  |  | High
Confirm Didier’s team have set up monitoring of live UG | General | JD | 2015-02-01 | No | High | Complete | JD advised task closed 09/02/2015.
Hijack issue - move UG onto 3rd server – liaise with Nick and Robin to get this set up | Project | JD |  |  | High
Install CAB Activity Viewer for Lyndon Place team | General | JD |  |  | High
Regenerate missing messages appearing on uncashed appointments report | Bug Fix | JD |  |  | High
Review UG escalation plan | General | JD |  |  | High
Set up Test and train UG environments and link to respective organiser versions | Project | JD |  |  | High
Expired schedules showing in UG via visual integration | Bug Fix | UltraGenda |  |  | Medium
HIV UG go-live | Project | SP |  |  | Medium
Radiology UG go-live | Project | SP |  |  | Medium
Rescheduling issue – logged with UltraGenda | Bug Fix | UltraGenda |  |  | Medium
Respiratory Physiology (GHH) UG go-live | Project | SL |  |  | Medium
Sonographers (GHH) UG go-live | Project | SP |  |  | Medium
Vascular re-design | Project | SL |  |  | Medium
Update mnemonic to GMC code | Feature Request | JD |  |  | Low
Self Check-In Pilot in Physiotherapy | Project | LW/NS/JD/UG Team | Apr-15 (pilot) |  | Medium
IST requirement - Out-Patient Utilisation monitoring | Project | TP/JD/UG Team | TBC |  | High
IST requirement - OP Forward Look reporting | Project | TP/JD/UG Team | TBC |  | High
IST requirement - Referral Timeliness reporting | Project | TP/JD/UG Team | TBC |  | High
IST requirement - Update to UG Appointment letters to highlight patient access policy | Project | TP/JD/UG Team | TBC |  | High
IST requirement - Implement Partial Booking across remaining specialties | Project | TP/JD/UG Team | TBC |  | High
IST requirement - Waiting list reporting | Project | TP/JD/UG Team | TBC |  | High
Waiting List
Add validation for Offered for admission Date and EROD fields | Bug Fix | JD | 2014-12-01 |  | High | Complete | JD advised task closed 26/01/2015.
Update invalid Offered for Admission Dates | Bug Fix | JD | 2014-12-01 |  | High | Complete | JD advised task closed 26/01/2015.
Automate coding per appointment type updates | Feature Request | JD |  |  | Medium
Diagnostic Suspension | Feature Request | JD |  |  | Medium | Complete | JD advised task closed 10/02/2015.
Enhance waiting list report | Feature Request | JD |  |  | Medium
PLCV report | Feature Request | JD |  |  | Medium
Prevent booking via W/L Scheduling Assistant into discharged episode | Bug Fix | JD |  |  | Medium
Show DNAs in Scheduling Assistant | Feature Request | JD |  |  | Medium | Complete | JD advised task closed 10/02/2015.
Referral Scanning
Add icon to indicate scanned letter/blank letter | Feature Request | JD |  |  | Medium
Cache Appointment Type drop down | Feature Request | JD |  |  | Medium
Prevent linking referral from Referral Scanning to IP spell | Bug Fix | JD |  |  | Medium
Prevent saving referral without linking to parent object | Bug Fix | JD |  |  | Medium
Prevent booking against minor PID | Bug Fix | JD |  |  | Low
Referral Scanning Zoom and Text size | Bug Fix | JD |  |  | Low
Partial Booking
Partial booking for Cardiology investigations | Project | SL |  |  | High
Open in UltraGenda to allow booking from Partial Booking waiting list | Feature Request | JD |  |  | Medium
Partial booking report enhancements for Bruce Fisher | Feature Request | JD |  |  | Medium
Update Partial Booking report to show PMS2 clock stops | Bug Fix | JD |  |  | Medium
PMS
Open clocks | Project | JD |  |  | High
Choose and book pathway with no spell - One off check to reunite pathway and spell | Bug Fix | JD |  |  | Medium | Complete | JD advised task closed 12/02/2015.
Closed Episodes not reopening on rollback from discharged to follow-up booked / required | Bug Fix | DH |  |  | Medium
Modify the mapper to create Planned Waiting List entries with stopped clocks |  | JD |  |  | Medium
Reporting
Build new report suite | General | JD |  |  | Medium
Enhance uncashed appointments report | Feature Request | JD |  |  | Medium
Identify sessions with pull list (report for Lynn Duggan) | General | JD |  |  | Medium
Organiser
Add link to scanned referral letter from organiser folder view | Feature Request | JD |  |  | Medium
Prevent booking from organiser list view - Phase 1 - Add warning | Feature Request | JD |  |  | Medium | Complete | JD advised task closed 10/02/2015.
Prevent booking from organiser list view - Phase 2 - Disable booking | Feature Request | JD | 2015-03-02 |  | Medium
Update folder view to show clock summary at pathway level | Feature Request | JD |  |  | TBC
Update folder view to show clock stops at discharge | Feature Request | JD |  |  | TBC
iCare
Add location parameter to ICE Interop integration | Feature Request | JD |  |  | Medium
Prevent faulty MSS message stopping HL7 parser | Bug Fix | JD |  |  | Low
Project
Reminder service | Project | JD |  |  | Medium
Ali Bahron (information provided on behalf of Dave Hextell, Head of ICT Systems Development) |  |  |  |  | (Last updated: | 08/01/2015)
Project / Activity - Systems Development | Category | Resource | Planned Completion | On ICT Request List? | Priority | Status | Update & Comments
Concerto Development
Concerto integration with Marie Curie Hospice |  | AB/PS |  | No |  | On-going
Chronic Kidney Disease (CKD) Concerto rollout (Supporting NHS England) |  | AB/PS |  | No |  | On-going
Acute Kidney Injury (AKI) Concerto rollout (also linked to Dendrite) |  | AB/PS |  | No |  | On-going
Medication and antibiotic dashboard and report |  | AB/PS |  | No |  | On-going
Clinical infection (also linked to Dendrite) |  | AB/PS |  | No |  | On-going
System Development
Citrix |  | AB |  | No
E-obs |  | AB/PS
Renal kidney monitor system (Hugh Rayner) |  | CSan |  | No |  | In progress
ADT |  | PS
PMS2 |  | PS
Shared Worklist Version 2 |  | PS
iBleep integration |  | PS
Requests system |  | PS
SQL rationalisation program |  | PS
Nagios Implementation |  | PS
NagVis implementation |  | PS
GP data integration (YCC) |  | PS
AGFA Xeroviewer (PACS viewer) |  | PS
Status Page V2 |  | PS
DART (Ideagen) |  | PS
Orbean Electronic Forms (E-Forms) implementation |  | PS
Rhapsody integration (clinical data repository messaging) |  | PS
Dendrite
RACP |  | JK |  | Yes |  | In progress
ONCDAYUNIT |  | JK | Awaiting date | No |  | In progress
Weight Management |  | JK |  | No |  | In progress
Pain Management |  | JK |  | No |  | In progress
NBSR |  | JK |  | No |  | In progress
ILD |  | JK |  | No |  | In progress
PHYSIO |  | JK | 2014-12-01 | No |  | In progress
ID |  | JK |  | No |  | In progress
NUTRITION |  | JK | 2014-12-01 | No |  | In progress
Cardiac Pathway |  | JK |  | No |  | In progress
PREOP |  | JK/CSan |  | No |  | In progress
Respiratory Physiology |  | JK | TBC | No |  | Planned
COSD XML Extract |  | JK | TBC | No |  | Planned
CF - Cystic Fibrosis registry |  | JK | TBC | Yes |  | Planned
RHEUMATOLOGY |  | JK | TBC | Yes |  | Planned
Support and Maintenance
TMIS maintenance and on-going updates |  | CSan | On-going |  |  | On-going
Long CNS and palliative care audit tools |  | CSan | On-going |  |  | On-going
TMIS access |  | IF | On-going |  |  | On-going
Concerto user licence management (leavers/starters) |  | IF | On-going |  |  | On-going
Touchpaper call monitoring and support |  | IF/PS | On-going |  |  | On-going
EPR (Concerto) technical - maintenance and monitoring |  | PS | On-going |  |  | On-going
SQL Cluster Architect (Database Hosting) |  | PS | On-going |  |  | On-going
SQL DBA technical lead - programming, maintenance and monitoring |  | PS | On-going |  |  | On-going
IIS web hosting - performance tuning and diagnostics |  | PS | On-going |  |  | On-going
Clinical information systems infrastructure |  | PS | On-going |  |  | On-going
Management of system support escalation |  | PS | On-going |  |  | On-going
Crystal reports (Galaxy, STARS and Touchpaper) |  | PS | On-going |  |  | On-going
Caroline Sadler, Head of ICT Programme Management and ICT Training |  |  |  |  | (Last updated: | 13/02/2015)
Project / Activity - Programme/Project Management | Category | Resource | Planned Completion | On ICT Request List? | Priority | Status | Update & Comments
Projects
ICT project prioritisation and request process | Project | CS/JB/LSi | End April 15 | No | High | In progress
PMS2 | Project | Project Office/Training | End April 15 | No | High | In progress
Digital Dictation/Clinical Letters | Project | CS/HP/LSi | TBC | No | Medium | In progress
SharePoint 2010 | BAU | LSi/LSa | On-going | No | BAU | In progress
Lilie Results Management | Project | CS/JB/SH | 2015-01-01 | No | High | In progress
DQ merge and reporting | BAU | CS/JB/LSa/DQ Team | On-going | No | BAU | On-going
MRS QA | BAU | CS/LSa/DQ Team | On-going | No | BAU | On-going
ICT PO Process Updates | Project | CS/JB/HP/LSi/LSa | 2015-06-01 | No | High | In progress
BHH Training Room relocation | Project | CS/KA | 2015-06-01 | No | Medium | In progress
Concerto Live Rollout | Project | CS | TBC | No | High | Not started
Climate | Project | CS/JB/SH/LSi/KA | 2015-03-01 | No | High | In progress
Ideagen | Project | CS/JB/LSi | 2015-04-01 | No | High | In progress
Xero Project (awaiting update) | Project | CS | TBC | No | TBC | On-hold
NHSMail Services | Project | CS/SK/SH | 2015-04-01 | No | High | In progress
Patient Check In Solution (awaiting update) | Project | CS | TBC | No | TBC | On-hold
Windows 2000 Server Decommission | Project | CS/JB/HP | 2014-12-01 | No | High | In progress
Your Care Connected (PoC) | Project | CS/JB/LSi/LSa | 2015-04-01 | No | High | In progress
ICT Systems and PMS Roadshow | Project | CS/JB/KA/HP/SK/LSi | 2015-03-01 | No | High | Not started
ICT Communications | Project | CS | TBC | No | High | On-going
Training
Concerto (Consultants) | Training BAU | KA/MW/EM | On-going | No | High | On request
Referral Scanning (Consultants) | Training BAU | KA/MW/EM | On-going | No | High | On request
Redesign Pathways Course | Training | KA | 2014-12-01 | No | High | In progress
Redesign Organiser (UG and WL) Courses | Training | KA/MW | 2014-12-01 | No | High | In progress
TNA | Training BAU | CS/KA | On-going | No | High | On-going
Pathways Training (PMS2) | Training | KA/MW/SMc/SH/LSi/LSa/EM | TBC | No | High | TBC
HISS (CNT, Amalg) | Training BAU | MW/SMc/SH/LSi/LSa/EM | On-going | No | High | On-going
PMS1/Organiser (OP Scheduler) | Training BAU | KA/MW/SMc/LSa/EM | On-going | No | High | On-going
PMS2/Organiser (ADT, WL, MPI) | Training BAU | KA/MW/SMc/LSa/EM | On-going | No | High | On-going
iCare EPR (Consultants) | Training BAU | KA/MW/EM | On-going | No | High | On request
Doctors Induction (Camtasia) | Training | KA/MW/SMc | 2015-04-01 | No | Medium | In progress
Web Based Clinical Letters | Training BAU | KA/MW/LSa/EM | On-going | No | High | On-going
Training Policies & Procedures | Training BAU | CS/KA | On-going | No | High | On-going
Training Documentation | Training BAU | KA/MW/SMc | On-going | No | High | On-going
LPI Accreditation | Training | KA/MW/SMc/EM | 2015-12-01 | No | Low | On-going
Migrate data from shared drive to SharePoint | Training | KA/MW/LSi/LSa/EM | 2015-02-01 | No | Medium | Complete | CS advised complete 09/02/2015.
Doctors Induction Process | Training BAU | KA/MW/SMc | On-going | No | Medium | On-going
New ICT Training Website | Training BAU | CS/KA | 2015-02-20 | No | High | In progress
Didier Meert, Head of ICT Technical Services |  |  |  |  | (Last updated: | 09/12/2014)
Project / Activity - Technical Infrastructure | Category | Resource | Planned Completion | On ICT Request List? | Priority | Status | Update & Comments
Maintenance
Network Refresh (P205) |  | MC | 2015-04-30 | No
Backups |  | PK |  | No
Backup Exchange |  | PK/NM |  | No
SQL - Snapmanager |  |  |  | No
Citrix Home drives |  | MC | 2014-11-28 | No
VM Cluster |  | MW |  | No
VM SQL Cluster |  | NM/PS |  | No
Server Patching |  | NM |  | No
Exchange 2010 Patching |  |  |  | No
UAG Decommission (219513) |  | SC |  | No
Wireless Controller/Ringmaster upgrade |  | PK |  | No
Agfa Server Reboots (216817) |  | SC |  | No
Vmware Updates/Patching Hosts |  |  |  | No
UCS Updates/Patching |  |  |  | No
Citrix Farm Updates |  |  |  | No
TS Departmental Requests
Dart Ideagen (197609) |  | NM/UK/PS | 2015-01-02 | No
Cardass (218535) |  |  |  | Yes
PorterTrack Upgrade (212347) |  | PK |  | Yes
Topcon Medisoft Migration (P230) |  | PK |  | No
E-Roster Upgrade (209271) |  | SC/PK | 2014-12-12 | No
E - Roster GO LIVE |  | SC/PK | 2015-01-16 | No
Telemedicine Stroke Pilot (216673) |  | SC |  | Yes
Solihull Dermatology Move (P225) |  |  |  | No
Chemotherapy (P224) |  |  |  | No
Cell Path (P222) |  | SR |  | No
Citrix Photoshop (219879) |  |  |  | No
Envoy (192179) |  | SC |  | Yes
Dawn 4s (192297) |  | SC |  | Yes
E-Delphyn (196596) |  | SC |  | Yes
Endobase server space (180225) |  |  |  | Yes
Viewpoint (171137) |  | PK | 2014-11-28 | No
Ophthalmology (218912) |  | SC
EP Shadow server refresh |  |  |  | Yes
SGUM HIV Climate (P184) |  |  |  | No
ICE upgrade |  | MW | 2014-12-26 | Yes
Intranet pg (220924) |  | UK |  | No
Citrix Proton Reflex (222246) |  |  |  | No
Othoview virtualise (222589) |  |  |  | No
Endpoint encryption (223828) |  |  |  | No
Badgernet ipads (P206) |  | SH |  | No
Npex VPN (P215) |  |  |  | Yes
Cas site SOL (216183) |  |  |  | No
OPAS replace server/citrix setup (203838) |  | SC |  | No
Teletracking (Estates) |  | PK |  | Yes
Badgernet failover testing (212353)
New AP GHH (215871) |  |  |  | No
Allergy Add-on to Menumark |  | PK |  | No
Hawthorn F/S migration |  | UK |  | No
Verafon (chip/pin services) |  | PK |  | No
Fileshare migration from BHHCX4001/02/03/04 to netapp Vfilers |  |  | 2015-05-29 | No
Migration of Backup servers to vFilers |  |  | 2014-12-30 | No
Estates Citrix Migration |  |  | 2014-12-30 | No
Vcops – Vmware monitoring tools |  |  | 2014-12-02 | No
New Sharepoint 2010/2013 Farm |  |  | 2014-11-25 | No
Sharepoint migration from 2003/2007/2010 to new Farm |  |  | 2014-12-30 | No
Retinal Screening Database migration to SQL 2012 |  |  | 2014-11-20 | No
Netapp – Snapshots/Snapvault/Snaplock |  |  |  | No
P2V of old physical servers to Vmware |  |  |  | No
Decommissioning of Physical Servers |  |  |  | No
ICT Sharepoint Site |  |  |  | No
Citrix EP App Updates |  |  |  | No
Telecomms Requests
Switchboard replacement (tender process) |  | LWa | 2017
Data cabinet and data fibre upgrades |  | LWa/SE | In progress
TS Requests
Touchpaper upgrade (216810) |  | PK |  | No
UltraGenda server (219508) |  | NM |  | No
Windows 7 upgrades (P138) |  | JC |  | No
GPO |  | UK |  | No
Shares |  | UK |  | No
Truecrypt USB admin access (217511) |  |  |  | No
Requests STD (on going process Wed to Wed) |  | UK/SC/MW | 2015-04-30 | No
Requests NON STD process (on going process) |  | SC | 2015-04-30 | No
Community share moves (220969) |  | NM |  | No
Citrix DR (GHH) |  | NM |  | No
Exchange2003 decommission |  | NM |  | No
MDM - MobileIron |  | PK |  | No
IIS Cloud (Win2K) |  | UK |  | No
Windows 8 (for tablets) |  | UK |  | No
Decommissioning of the Win2003 Servers
Switch-off Sharepoint 2003/2007 setup
Lee Wootton, Head of ICT Business Delivery |  |  |  |  | (Last updated: | 06/02/2015)
Project / Activity - New ICT Business | Category | Resource | Planned Completion | On ICT Request List? | Priority | Status | Update & Comments
TPP SystmOne
Mobile working |  | JJ | On-going |  | High | On-going
Integrated word |  | JJ | End Mar 2015 |  | Medium | On-going
Service data recording and realignment (IC/Virtual wards/Comm Nurses) |  | NW |  |  | High | Not Started
E-referrals |  | JJ | End Dec 2014 |  | Medium | On-going
E-learning development |  | JJ | On-going |  | Low | On-going
Electronic blood requests (ICE link to Marie Curie & Derm) |  | JJ | End Mar 2015 |  | Medium | On-going
Strategic shared admin |  | JJ | End Mar 2015 |  | Low
LAC auto sharing of records |  | JJ | End Dec 2014 |  | Low
Children's and young persons dataset review |  | NW | End Mar 2015 |  | Medium
SystmOne training |  | JJ/NW | On-going |  | Low
Ad-hoc SystmOne change requests |  | JJ/NW | On-going |  | Medium
Management of electronic adopted records |  | JJ |  |  | Low
Sexual Health Mobilisation & Transition |  | LW | on-going |  | High | On-going
Endobase Implementation |  | LW/NS | on-going |  | High | On-going
Data Quality Strategy Development |  | LW | On-going |  | High
ICT Strategy Development |  | LW |  |  | High
SystmOne Exit & Transition |  | LW | On-going |  | High | On-going
Genomics Project |  | LW | On-going |  | Medium | On-going
Your Care Connect |  | LW/JB/AB/KA | On-going |  | High | On-going
ICT Request Process & Co-ordination |  | LW | On-going |  | Medium
Window 7 Replacement Community |  | LW | 2015-04-01 |  | High | On-going
CAMMHs Transition |  | LW | On-going |  | High | On-going
Urgent Care Centre Solihull |  | LW | On-going |  | Medium | On-going
Utilisation Tool Procurement |  | LW/AB | 2015-03-01 |  | Medium | On-going
Solihull migration to Heft Infrastructure |  | LW/DM | 2015-06-01 |  | Medium | On-going
Patient Self Check-in |  | LW/NS |  |  | Medium | On-going
Stroke Telemedicine Pilot |  | LW/SC | 2015-02-01 |  | Low | On-going
Dropbox Replacement |  | LW/DM/AB |  |  | High | On-going
VNA |  | LW/DM |  |  | Low
Solihull ICAS |  | LW |  |  | Medium
Child Protection-Information Sharing |  | LW/NS |  |  | Medium
Stock Management Control System |  | LW |  |  | Medium
Marie Curie System Access |  | LW | 2015-02-01 |  | low
Children + Young people's health service secondary uses data set |  | LW/NW |  |  | Medium
ICT Policy Review and Development |  | AB | On-going |  | Medium
Corporate Records Audit |  | AB/LW | 2015-03-01 |  | Medium
Information Risk Management (Asset Register, Training etc..) |  | AB/LW | On-going |  | Medium
Compliance Assessment & Assurance for New Systems |  | AB | On-going |  | Medium
NHSMail SMS & Fax Replacement - Community |  | LW | 2015-03-01 |  | Medium
Privacy Impact Assessments & Data Processing |  | AB | On-going |  | Medium
Information Security Risk Assessments |  | AB | On-going |  | Medium
Protocols with SystmOne |  | JJ | On-going |  | Medium
Lynn Duggan, Head of Medical Records |  |  |  |  | (Last updated: | 27/01/2015)
Project / Activity - Records Management | Category | Resource | Planned Completion | On ICT Request List? | Priority | Status | Update & Comments
Medical Records
Medical Records Scanning (current and future phases) | Project | LD | On-going |  |  |  | Re-commencement date TBC.
Review and Destruction of Marston Green Medical Records | BAU | SK/CS/IJ | 2015-02-01 |  |  |  | Review undertaken and Risk Assessment complete. Records to be retained for a further 3 years.
Redesign of departmental Appraisal process and paperwork | BAU | SD/KW/JS | 2015-06-01 |  |  |  | Review of JD’s against NHS National Profiles undertaken next meeting 17th Feb 2015.
Medical Records Storage - Relocation of lilac folders | BAU | SD/SK/KW/LD | On-going |  |  |  | Review of storage position on-going.
Access to Health policy/procedure for updating electronic records | BAU | SD/MO | 2015-03-01 |  |  |  | Review undertaken next meeting 18th Feb 2015.
Redesign of Access to Health data capture tool and relevant policy | BAU | SD/MO | 2015-04-01 |  |  |  | Review of current practice undertaken next meeting 18th Feb 2015.
Monitoring and relocating medical records to ease storage/space constraints due to cessation of scanning | BAU | SD/SK/LD/KW | On-going |  |  |  | On-going reviews taking place.
Review and implementation of Management training and development programmes | BAU | SD/SK/JS | 2015-04-01 |  |  |  | Outline of first level management position complete, next review 19th Feb 2015.